## Stakeholder Plan
Communication Plan <<examples provided below, amend to suit requirements>>
Communication type | Objective of communication | Medium | Frequency | Audience | Owner | Deliverable | Format | Comments
Kick off Meeting | Introduce the project team and the project. Review the project objectives and management approach. | Face to face | Once | Project Sponsor Project Team Stakeholders | Project Manager | Agenda Meeting minutes | Eg. Soft copy saved in drive / archived on SharePoint site
Project Team Meeting | Review status of the project with the team | Face to face Conference call | Weekly | Project Team | Project Manager | Agenda Meeting minutes Project schedule
Monthly Project Status Meeting | Report on the status of the project to management | Face to face Conference call | Monthly | Project Sponsor Project Director | Project Manager | Project update report Slide updates Data |  |  | Low | Advocate
Data Working Group | Identify KPI's, develop data set and reports | Face to face | Weekly | Working group | Technical Lead | Data set and report |  |  | Medium | Supporter
Project Status Reports | Report the status of the project including activities, progress, costs and issues | Email | Monthly | Project Sponsor Project Director Project Team Stakeholders | Project Manager | Project status report |  |  | High | Neutral
Critic
Blocker