## Gantt Chart
Health service review, assessment, and planning process |  |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
[5 empty] | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy | dd/mm/yy
Ref | Activity | Lead | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
1 | Review current service |  | 1 | 11
1.1 | Determine scope, process, approach, expectations. |  | 1 | 1
1.1.1 | Confirm with HHS Executive and/or Board, expectations, discuss process, approach, and level of support required. |  | 1 | 1
1.1.2 | Identify resource to lead review and assessment |  | 1 | 1
1.2 | Establish governance and steering committee |  | 1 | 1
1.2.1 | Hold Steering committee meetings fortnightly |  | 2 | 26
1.3 | Create stakeholder engagement and consultation plan |  | 1 | 2
1.4 | Collect and analyse data and service information · Describe current health service map · Prepare workforce profile · Assess service system risks · Prepare summary report |  | 2 | 6
1.5 | Engagement and consultation with stakeholders |  | 3 | 8
1.5.1 | Prepare consultation material |  | 3 | 6
1.5.2 | Consumer and community consultation |  | 7 | 9
1.5.3 | Clinician consultation |  | 7 | 9
1.6 | Report on findings |  | 9 | 16
1.6.1 | Compile report |  | 9 | 12
1.6.2 | Deliver report and recommendations to HHS Exec for approval |  | 13 | 14
1.6.3 | Progress through governance process for approval to change scope/enhance service as required |  | 15 | 16
1.6.4 | Feedback findings to all stakeholders |  | 17 | 18
2 | Plan (re)design of health service |  | 18 | 26
2.1 | Develop plan for co-designing health services · Identify resource to lead planning and co-design project · Review Steering Committee membership and update if required · Review and update stakeholder engagement and communication plan |  | 18 | 20
2.2 | Design health service |  | 20 | 26
2.2.1 | Engage with stakeholders to develop options |  | 20 | 21
2.2.2 | Feedback to stakeholders on assessment and prioritisation of options |  | 22 | 23
2.2.3 | Finalise plan for health services |  | 22 | 25
3 | Follow HHS and Department (if appropriate) approval processes to implement planned changes to service |  | 26 | ? | [25 empty] | ►